## Sheet1
Issues
present modal telling users why we need location before asking for location auth
If location isn't enabled offer URL to take user directly to settings
What to do in event my Consumer prepare for segue fails bc it has wrong identifier?
Image of hand overflowing is only 1x (image not icon) same with image of hearts
Vendor Home page says Welcome Back ABC Catering and needs to say Vendor Name Instead
Vendor posts must be editable
set default food image
Users text in text fields should be black and not bold
All the cells need to be rounded
All the buttons need to be rounded and have shadows

## Sheet2
Issue | Priority | Status
Autolayout | high
Notifications | high
Vendor needs to set duration of post based on picker views | med
Users can change location to change seen posts | med/high
Vendor selects current location/location for food is set to location they type in | med
Keyboard adjustments needed on signup screens | low
Ability to delete/edit food | low
User can message vendor | low
What happens after Vendor hits accept or reject to consumer's request?
Only show users "Open" posts | high | Complete
Add user roles to signup | high | Complete
Fix location request | med | Complete
Add user images to food | med | Complete
Change TableViews to CollectionsViews so you can add space between cells | med | Complete
QUESTIONS:
What happens if there are no current posts in your area (and assuming I have no error message up for this) - does nothing show up on the table view. What if you clicked a cell? Would it transition?
If I wanted to throw out an error and crash the program (such as in the case above where a user selects an empty cell and the tableview transitions anyway and there is no current post selected, how do I do this?
Say 2 users are looking at the same post at the same time and while they're on the post detail page one of them requests it, how can I check for this when the other hits request? (Do I check when they hit request to see if it's open or is it better when the first user is looking at it to not even show it? If I do that second method how do I stop things from constantly dissapearing from user 2's home screen)
Where do I save user sent messages to?

## Sheet3
Name | Email | UID | Address | Latitude | Longitude
Prestige Caterers | test2@gmail.com | 79QrInIEbzb8uIdJjoaLz4SIWEh2 | 111 Irving Place, Woodmere, NY 11598
Simply Divine Catering | test3@gmail.com | VbMfupaFL0bf3ki1jGVwFJqZkOv2 | 334 Amsterdam Ave, New York, NY, 10023
Harlem Food Bank | test101@gmail.com | h2VRZh8n43f5gNrmGjsdkBj5sS63 | 252 W116th St, New York, NY 10026 | 40.8042 | 73.955
Food Bank for New York City | test102@gmail.com | ZPUv5TRYcFgEYONYn3C8VoktAND3 | 39 Broadway, New York, NY 10038
My Apartment |  |  |  | 40.7961 | -73.9692